## Summary
CW-150 Migration, UAT & Cutover Control
Formula-driven control sheet. No Production migration is authorized by this workbook.
Control KPI | Value | Gate | Owner | Required evidence | Status | Decision date
Migration objects | 28 | Data mapping approved | Business owners | Signed mapping + source extract | Not Started
Objects accepted | 0 | Dry run reconciled | Migration Lead / Finance | Import logs + reconciliation | Not Started
Reconciliation failures | 0 | Golden UAT signed | Process owners | Scenario evidence | Not Started
UAT scenarios passed | 0 | Pilot / parallel run accepted | Steering Committee | Pilot sign-off | Not Started
Open critical issues | 0 | Production cutover approval | Executive Sponsor | Go / No-Go minutes | Blocked
Cutover gates complete | 0
Operating rule | Details
Environment | All imports and module upgrades run on Development/Staging first.
Financial safety | Do not post invoices, bills, journal entries, payments, taxes, or opening balances without explicit approval.
Data preservation | Approved/posted documents are corrected by revision, reversal, cancellation, or credit note—not deletion.
Cutover | Production remains blocked until dry run, reconciliation, role UAT, pilot, backup, and signed Go/No-Go are complete.

## Migration Register
Migration Object Register
Complete in dependency order. Status Accepted requires mapping, dry run, counts, reconciliation and owner sign-off.
Seq | Object | Odoo model / route | Business owner | Source file / system | Mapping status | Dry-run status | Source rows | Imported rows | Rejected rows | Count variance | Acceptance
1 | Companies | res.company |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
2 | Branches | res.company / branch configuration |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
3 | Users | res.users |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
4 | Partners | res.partner |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
5 | Product Categories | product.category |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
6 | Products / Resources | product.template |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
7 | Units of Measure | uom.uom |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
8 | Cost Codes | mu.construction.cost.code |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
9 | WBS Templates | mu.construction.wbs |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
10 | Locations / LBS | mu.construction.location |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
11 | Warehouses / Stock Locations | stock.warehouse / stock.location |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
12 | Equipment | maintenance.equipment / fleet.vehicle |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
13 | Contracts | mu.construction.contract |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
14 | Projects | project.project |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
15 | BOQs | mu.construction.boq / line |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
16 | Budget Baselines | mu.construction.budget.baseline / line |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
17 | Open Purchase Orders | purchase.order |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
18 | Open Subcontracts | purchase.order (subcontract) |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
19 | Inventory Balances | stock inventory adjustment |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
20 | Customer Advances | account.move / reconciliation |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
21 | Supplier / Subcontract Advances | account.move / reconciliation |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
22 | Retention Receivable | opening financial migration |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
23 | Retention Payable | opening financial migration |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
24 | Guarantees | mu.construction.guarantee |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
25 | Open IPCs | mu.construction.client.ipc |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
26 | Open Vendor Bills | account.move |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
27 | Opening Accounting Balances | account.move |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started
28 | Documents | documents.document |  |  | Not Started | Not Started | 0 | 0 | 0 | 0 | Not Started

## Reconciliation
Migration Reconciliation
Enter source and Odoo totals after each dry run. Tolerance must be explicitly approved; default is zero.
Control | Source register | Odoo source of truth | Source total | Odoo total | Tolerance | Result | Owner | Evidence | Sign-off date
Inventory = GL | Inventory valuation extract | Stock Valuation vs Inventory GL | 0 | 0 | 0 | PASS
AR = Aging | Customer aging | Receivable ledger / aging | 0 | 0 | 0 | PASS
AP = Aging | Supplier aging | Payable ledger / aging | 0 | 0 | 0 | PASS
Retention Receivable | Contract retention register | IPC deductions / receivable | 0 | 0 | 0 | PASS
Retention Payable | Subcontract retention register | Certificate deductions / payable | 0 | 0 | 0 | PASS
Advances | Advance registers | Advance accounts and contracts | 0 | 0 | 0 | PASS
Project Actuals | Legacy project cost | Analytic ledger | 0 | 0 | 0 | PASS
Open Commitments | Open PO / subcontract | Remaining commitments | 0 | 0 | 0 | PASS
Certified | IPC register | Certified IPCs | 0 | 0 | 0 | PASS
Billed / Collected | Invoice and receipt registers | Invoices and reconciled payments | 0 | 0 | 0 | PASS

## UAT Scenarios
Golden UAT Scenarios
Execute on named pilot users with evidence. Financial posting steps remain manual and require Finance authorization.
ID | Scenario | Scope | Business owner | Tester | Evidence link / reference | Defect ID | Status | Sign-off date | Notes
GS-01 | Tender to Award | Lead → Tender → BOQ → Estimate → Bid Approval → Award → Project Bootstrap |  |  |  |  | Not Started
GS-02 | Procure to Consume | MR / stock check → RFQ → PO → Receipt → MIR → Issue → Consumption → Bill / payment control |  |  |  |  | Not Started
GS-03 | Subcontract to Pay | Subcontract BOQ → Advance → Measurement → Certificate → Retention / recovery → Draft Bill → Release |  |  |  |  | Not Started
GS-04 | Measure to Cash | WIR → Measurement → IPC → Deductions → Draft Invoice → ETA readiness → Collection tracking |  |  |  |  | Not Started
GS-05 | Variation / Claim / EOT | RFI → Potential Change → Notice → Estimate → Approval → Contract / budget update |  |  |  |  | Not Started
GS-06 | Monthly Close and Closeout | Commitment / Actual / Accrual → ETC/EAC/WIP → Dashboard → Handover → DLP → Final Account |  |  |  |  | Not Started

## Cutover Checklist
Controlled Cutover Checklist
Go/No-Go is blocked until every mandatory gate is Complete and evidence is attached.
Seq | Gate / activity | Environment | Owner | Mandatory | Status | Evidence / reference | Rollback trigger
1 | Staging clone refreshed | Staging | Technical Lead | Yes | Not Started
2 | Approved configuration baseline applied | Staging | Functional Lead | Yes | Not Started
3 | All custom modules tested | Development / Staging | Technical Lead | Yes | Not Started
4 | Functional UAT signed | Staging | Process Owners | Yes | Not Started
5 | Pilot project completed | Staging | Project Sponsor | Yes | Not Started
6 | Parallel run reconciled | Staging | Finance / Operations | Yes | Not Started
7 | Security and SoD approved | Staging | Security Owner | Yes | Not Started
8 | Arabic / RTL and reports accepted | Staging | Business Owners | Yes | Not Started
9 | Migration dry run accepted | Staging | Migration Lead | Yes | Not Started
10 | Production backup verified | Production | Odoo.sh Owner | Yes | Not Started
11 | Go / No-Go approval recorded | Governance | Executive Sponsor | Yes | Not Started
12 | Controlled module deployment | Production | Technical Lead | Yes | Not Started
13 | Opening data migration | Production | Migration / Finance | Yes | Not Started
14 | Smoke test and reconciliation | Production | UAT Leads | Yes | Not Started
15 | Hypercare opened | Production | Support Lead | Yes | Not Started
16 | Post-go-live review | Production | Steering Committee | Yes | Not Started

## Master Data
Master Data Import Staging
Use stable external IDs and company/project codes. This sheet is a staging template, not a direct import authorization.
Object type | External ID | Company code | Record code | Name | Parent external ID | Currency | Language | Effective from | Effective to | Active | Source reference | Validation status
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked
[10 empty] | TRUE |  | Not Checked

## Projects Contracts
Project and Contract Import Staging
Projects must link to an approved company, analytic account and contract context before dependent BOQ or transaction loads.
External ID | Project code | Project name | Company code | Analytic account code | Contract external ID | Contract type | Partner external ID | Currency | Original value | Start date | End date | State | Validation status
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked
[9 empty] | 0 |  |  | Draft | Not Checked

## BOQ Budget Lines
BOQ and Budget Line Staging
One row per source line. Preserve external IDs, revision, WBS, cost code, location and currency context.
BOQ external ID | Revision | Line external ID | Parent section ID | Project code | Contract external ID | BOQ type | Item code | Description | UoM | Quantity | Unit rate / cost | Amount check | WBS code | Cost code | Validation status
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked
| 0 |  |  |  |  | Sell |  |  |  | 0 | 0 | 0 |  |  | Not Checked

## Open Transactions
Open Transaction Staging
Load only open, reconciled source positions after the related master data. Draft standard documents remain under Finance/Operations control.
Document type | External ID | Company code | Project code | Contract external ID | Partner external ID | Document date | Due date | Currency | Gross amount | Open amount | Source state | Source reference | Validation status
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked
[9 empty] | 0 | 0 |  |  | Not Checked

## Opening Balances
Opening Balance Staging — Approval Required
HIGH RISK: do not import or post until Finance approves accounts, journals, dates, currencies, analytic dimensions and reconciliation.
Batch | Line external ID | Company code | Journal code | Accounting date | Account code | Partner external ID | Currency | Amount currency | Debit | Credit | Project code | Analytic account | Cost code | Source reference | Approval status
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked
[8 empty] | 0 | 0 | 0 |  |  |  |  | Blocked

## Issue Log
UAT and Hypercare Issue Log
Use one issue per row with reproducible evidence and an owner. Critical issues block cutover until closed or formally waived.
Issue ID | Phase | Severity | Process / module | Description | Owner | Due date | Status | Resolution / evidence | Closed date
ISS-001 | UAT | Medium |  |  |  |  | Open
ISS-002 | UAT | Medium |  |  |  |  | Open
ISS-003 | UAT | Medium |  |  |  |  | Open
ISS-004 | UAT | Medium |  |  |  |  | Open
ISS-005 | UAT | Medium |  |  |  |  | Open
ISS-006 | UAT | Medium |  |  |  |  | Open
ISS-007 | UAT | Medium |  |  |  |  | Open
ISS-008 | UAT | Medium |  |  |  |  | Open
ISS-009 | UAT | Medium |  |  |  |  | Open
ISS-010 | UAT | Medium |  |  |  |  | Open
ISS-011 | UAT | Medium |  |  |  |  | Open
ISS-012 | UAT | Medium |  |  |  |  | Open
ISS-013 | UAT | Medium |  |  |  |  | Open
ISS-014 | UAT | Medium |  |  |  |  | Open
ISS-015 | UAT | Medium |  |  |  |  | Open
ISS-016 | UAT | Medium |  |  |  |  | Open
ISS-017 | UAT | Medium |  |  |  |  | Open
ISS-018 | UAT | Medium |  |  |  |  | Open
ISS-019 | UAT | Medium |  |  |  |  | Open
ISS-020 | UAT | Medium |  |  |  |  | Open
ISS-021 | UAT | Medium |  |  |  |  | Open
ISS-022 | UAT | Medium |  |  |  |  | Open
ISS-023 | UAT | Medium |  |  |  |  | Open
ISS-024 | UAT | Medium |  |  |  |  | Open
ISS-025 | UAT | Medium |  |  |  |  | Open
ISS-026 | UAT | Medium |  |  |  |  | Open
ISS-027 | UAT | Medium |  |  |  |  | Open
ISS-028 | UAT | Medium |  |  |  |  | Open
ISS-029 | UAT | Medium |  |  |  |  | Open
ISS-030 | UAT | Medium |  |  |  |  | Open